## Foglio1
Month | 5 | 5..6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7..8 | 8 | 8 | 8 | 8..9 | 9 | 9 | 9 | 9 | 9..10 | 10 | 10 | 10 | 10..11 | 11 | 11 | 11 | 11..12 | 12 | 12 | 12 | 12
Week | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
SWAMP deliverables
D25- Smart water management application | [23 empty] | D25
Papers
ACM-IoT:SEPA FIWARE
From raw MQTT message to SOSA and context (ISWC)
SEPA UHP
Modeling Strategies for IoT Systems (Filev)
NGSI-LD
JSON-LD API
NGSI-LD HTTP API
D25- Smart water management application
Weather data
ACL e oauth
CBEC database integration
LAI input form
Criteria integration
Canal levels
Water distribution scheduling (Alessio)
App richiesta irrigua manuale
Aggiornare App di calibrazione
SEPA UHP
Update processor A&R
LUTT filtering
Broken subscriptions, last will, testament
Morandi+Live data in memory (JENA)
Dissemination
Aggiornamento GitHub
Pubblicazione su SPARQL 1.2 forum
SEPA as a SERVICE
MQTT agent
Historical logger
Embraba probe data on SEPA View
Note on AG9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Penso che almeno la parte che non riguarda i test si possa già riprendere e completare a luglio. Escluderei giugno perchè (almeno per quanto riguarda me e fra) abbiamo da completare un paper su rivista con turchet e uno su rivista con miguel... in più ora stiamo preparando materiale con l'infn per una conferenza in Australia bella tosta Reply: Dobbiamo allora spostare. Tra l'altro è diventato prioritario lo sviluppo di APP per SWAMP e quindi l'attività su SEPA UHP lo sposto più avanti. Prima del paper bisogna implementare quella parte